## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to the project (Cyber Risk Assessment & Threat Intelligence Platform) | SHOULD HAVE | No Dependency | RAGUL | 3- Completed
S1 | S1 | US-002 | Project understanding, requirement analysis, and environment setup | SHOULD HAVE | No Dependency | RAGUL | 3- Completed
S2 | S2 | US-003 | Research on cyber risk scoring concepts and vulnerability metrics (CVE, CVSS) | SHOULD HAVE | Knowledge about it | RAGUL | 3- Completed
S2 | S2 | US-004 | Study of GenAI-based chatbot architecture for cybersecurity use cases | SHOULD HAVE | Knowledge about it | RAGUL | 3- Completed
S3 | S3 | US-005 | Setup Streamlit environment and create basic chatbot UI structure | MUST HAVE | Streamlit | RAGUL | 3- Completed
S3 | S3 | US-006 | Design user-friendly chat interface to accept vulnerability-related queries | MUST HAVE | Streamlit | RAGUL | 3- Completed
S4 | S4 | US-007 | Load and process vulnerability data from JSON file for chatbot context | MUST HAVE | JSON Data | RAGUL | 3- Completed
S4 | S4 | US-008 | Integrate OpenRouter API for AI-based responses using vulnerability context | MUST HAVE | API Key | RAGUL | 3- Completed
S5 | S5 | US-009 | Optimize chatbot response handling and manage session-based chat history | MUST HAVE | AI Integration | RAGUL | 3- Completed
S5 | S5 | US-010 | Perform testing, prepare demo video, and present chatbot functionality to team | MUST HAVE | Chatbot integration module | RAGUL | 3- Completed
S6 | S6 | US-011 | Preparing the technical documents and presentation (ppt) for the project | SHOULD HAVE | Dependency | ALL TEAM | 3- Completed
S7 | S7 | US-012 | Finalizing the technical documents and presentation (ppt) for the project | SHOULD HAVE | Dependency | ALL TEAM | 3- Completed
S8 | S8 | US-013 | Final project demonstration completed and project files uploaded to GitHub repository | SHOULD HAVE | Github,VScode | RAGUL | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7